## EUCL PP 2024-2025 DRAFT
Department | No | Tender Title | Estimated budget | Source of Funds | Meth | Tender Doc Preparation | Publication | opening | Start Evaluation | End evaluation | Final Notification | Contract Signature Date |  | Supervision | Prio study
GENERATION | 1 | Purchase PLC system for Mukungwa HPP | 400000000 | EUCL | ICB | 2024-08-01 | 2024-08-22 | 2024-09-21 | 2024-09-21 | 2024-10-12 | 2024-11-02 | 2024-11-23 | 114 | NO | NA
GENERATION | 2 | Tender for Maintenance service of radial gate at dam | 300000000 | EUCL | NCB | 2024-08-01 | 2024-08-22 | 2024-09-21 | 2024-09-21 | 2024-10-12 | 2024-11-02 | 2024-11-23 |  | NO | NA
GENERATION | 3 | Provision of meal/Lunch at thermal power plants | 57215937 | EUCL | NCB | 2025-01-01 | 2025-01-22 | 2025-02-21 | 2025-02-21 | 2025-03-14 | 2025-04-04 | 2025-04-25 |  | NO | NA
GENERATION | 4 | Supply of milk at power plants | 47088000 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
GENERATION | 5 | Contract for selling of sludge from power plants | 0 | EUCL | REOI | 2024-12-01 | 2024-12-22 | 2025-01-21 | 2025-01-21 | 2025-02-11 | 2025-03-04 | 2025-03-25 |  | NO | NA
GENERATION | 6 | Framework contract for TV subscription | 1500000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
GENERATION | 7 | Purchase of Spare parts for Nyabarongo HPP | 120000000 | EUCL | SS | 2024-09-01 | 2024-09-22 | 2024-10-22 | 2024-10-22 | 2024-11-12 | 2024-12-03 | 2024-12-24 |  | NO | NA
CORPORATE SERVICES | 8 | Repair and Maintenance of Office Furnitures | 43800000 | EUCL | NCB | 2025-04-01 | 2025-04-22 | 2025-05-22 | 2025-05-22 | 2025-06-12 | 2025-07-03 | 2025-07-24 |  | NO | NA
CORPORATE SERVICES | 9 | Supply of Construction materials | 150000000 | EUCL | NCB | 2024-08-01 | 2024-08-22 | 2024-09-21 | 2024-09-21 | 2024-10-12 | 2024-11-02 | 2024-11-23 |  | NO | NA
CORPORATE SERVICES | 10 | Cleaning expenses | 144944164 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
CORPORATE SERVICES | 11 | New Air Conditioners and Maintenance of those in place | 170261200 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
CORPORATE SERVICES | 12 | Purchasse of tyres | 95000000 | EUCL | NCB | 2025-01-01 | 2025-01-22 | 2025-02-21 | 2025-02-21 | 2025-03-14 | 2025-04-04 | 2025-04-25 |  | NO | NA
CORPORATE SERVICES | 13 | Office stationary | 120000000 | EUCL | NCB | 2024-08-01 | 2024-08-22 | 2024-09-21 | 2024-09-21 | 2024-10-12 | 2024-11-02 | 2024-11-23 |  | NO | NA
CORPORATE SERVICES | 14 | Clearing Services | 6000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
CORPORATE SERVICES | 15 | Renting of EUCL premises | 494000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
CORPORATE SERVICES | 16 | Feacal Sludge collection | 10000000 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
CORPORATE SERVICES | 17 | Contract for Tempolary Manpower, Equipment, Civil Materials and New connections | 1526820257 | EUCL | SS | 2025-03-01 | 2025-03-22 | 2025-04-21 | 2025-04-21 | 2025-05-12 | 2025-06-02 | 2025-06-23 |  | NO | NA
COMMERCIAL | 18 | Supply of Postpaid MV Metering Unit 30kv and 15 Kv | 45000000 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
COMMERCIAL | 19 | Supply of Smart Prepaid High Current meters (200, 300,400, 500, 600, 800, 1000 Amps) and smart post paid meters including accessories | 820000000 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
COMMERCIAL | 20 | Supply of Three phase prepaid meters 100A | 1040000000 | EUCL | NCB | 2025-04-01 | 2025-04-22 | 2025-05-22 | 2025-05-22 | 2025-06-12 | 2025-07-03 | 2025-07-24 |  | NO | NA
COMMERCIAL | 21 | Supply of Single Phase prepayment Meters 80A | 3110829737 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23
TRANSMISSION | 22 | High Voltage Transmission Line Maintenance including spare parts materials (110 & 220 kVTowers, Overhead conductors,insulators, earthing materials,etc). | 600000000 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
TRANSMISSION | 23 | Procurement of : a) T-Socket cable termination kits (Extendable type), b) Cable termination kits Type 1 size 2 for 30kV and 15kv switchgears, c) Cable termination kits Type 2 size 1 for 30kV and 15kv switchgears, d) 110kV cable termination kits for 110kV underground copper cables 1*240sqmm, | 100000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 24 | High Voltage Substation Maintenance including spare parts (MV and LV equipment_Framework Contract with ABB for supply of spare parts and technical support). | 250000000 | EUCL | SS | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 25 | Acquisition of Mobile Generators (10KVA) for Substations maintenance works | 20000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 26 | Procurement of different spare parts (motor drive, tripping/closing/blocking coils for CBs and Disconnectors, gaskets for power transformers, heaters, etc ) for High Voltage/Medium Voltage Substations. | 135000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 27 | Purchase of batteries, battery chargers and related spare parts for the 110V DC supply | 150000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 28 | Purchase of Protection relays to replace the malfunctioning ones | 180000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 29 | Purchase of protection system maintenance Parts | 50000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 30 | Testing equipement`s softwares and licenses | 100000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 31 | Testing Equipment and toolbox | 127555000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 32 | RTU and Maintenance Spare parts & Tools | 100000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 33 | Purchase of spare parts for upgrade of RTU/Gateway and Substation Human Machine Interfaces for 5 sites | 150000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
TRANSMISSION | 34 | Supply and installation of backup Generators in Substations | 400000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
DISTRIBUTION | 35 | Repair & replace damaged MV & LV cables ( ABC cable&UG cables) | 450000000 | EUCL | NCB | 2024-08-01 | 2024-08-22 | 2024-09-21 | 2024-09-21 | 2024-10-12 | 2024-11-02 | 2024-11-23 |  | NO | NA
DISTRIBUTION | 36 | Maintenance of existing Auto-reclosers (i.e Battery & UPS with poor performance capacity,other accessories) | 95000000 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
DISTRIBUTION | 37 | O&M of standby generators and UPS and Testing Equipment | 50000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
DISTRIBUTION | 38 | Purchase new LED lamps & various electrical materials for street lights O&M ( i.e cables, timers, contactors, Lux meters, etc) | 90000000 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
DISTRIBUTION | 39 | Repair services of defected LED lamps | 70000000 | EUCL | NCB | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
PLANNING | 41 | Safety signs and labels for cabins, substations and power plants | 20000000 | EUCL | SS | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
PLANNING | 42 | Purchase of catridges, papers, GNSS antenna handle | 6000000 | EUCL | SS | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
PLANNING | 43 | Tender for safety tools and equipment | 64000000 | EUCL | SS | 2024-07-01 | 2024-07-22 | 2024-08-21 | 2024-08-21 | 2024-09-11 | 2024-10-02 | 2024-10-23 |  | NO | NA
IT SERVICES | 44 | Framework contract for supply of network equipment | 200000000 | EUCL | NCB | 2025-03-01 | 2025-03-22 | 2025-04-21 | 2025-04-21 | 2025-05-12 | 2025-06-02 | 2025-06-23 |  | NO | NA
IT SERVICES | 45 | Tender for supply of routers,access points,wireless controller,etc | 160000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
IT SERVICES | 46 | Tender for acquisition of IT consumables | 50000000 | EUCL | NCB | 2024-08-01 | 2024-08-22 | 2024-09-21 | 2024-09-21 | 2024-10-12 | 2024-11-02 | 2024-11-23 |  | NO | NA
IT SERVICES | 47 | Purchase of MS Licences | 500000000 | EUCL | NCB | 2025-07-15 | 2025-08-05 | 2025-09-04 | 2025-09-04 | 2025-09-25 | 2025-10-16 | 2025-11-06 |  | NO | NA
IT SERVICES | 49 | System Licensing and Subscription - MDM/AMI | 88400000 | EUCL | SS | 2025-04-01 | 2025-04-22 | 2025-05-22 | 2025-05-22 | 2025-06-12 | 2025-07-03 | 2025-07-24 |  | NO | NA
IT SERVICES | 50 | Procurement of Data analytics tool | 30000000 | REG | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
IT SERVICES | 51 | Purchasing of 2 Label Printer CL-E720 | 6000000 | EUCL | NCB | 2024-10-02 | 2024-10-23 | 2024-11-22 | 2024-11-22 | 2024-12-13 | 2025-01-03 | 2025-01-24 |  | NO | NA
COMMUNICATION/ EXTERNAL LINK REG | 52 | Tender for supply of promotional Materials | 200000000 | REG | NCB | 2025-04-01 | 2025-04-22 | 2025-05-22 | 2025-05-22 | 2025-06-12 | 2025-07-03 | 2025-07-24 |  | NO | NA
COMMUNICATION/ EXTERNAL LINK REG | 53 | Tender for Media houses | 100000000 | REG | NCB | 2025-01-15 | 2025-02-05 | 2025-03-07 | 2025-03-07 | 2025-03-28 | 2025-04-18 | 2025-05-09 |  | NO | NA
HR | 54 | Tender for provision of Sports services for REG and EUCL staff | 90000000 | EUCL | SS | 2025-03-01 | 2025-03-22 | 2025-04-21 | 2025-04-21 | 2025-05-12 | 2025-06-02 | 2025-06-23 |  | NO | NA
HR | 55 | Tender for provision of Sports services for REG and EUCL Senior Managers | 30000000 | EUCL | SS | 2025-03-01 | 2025-03-22 | 2025-04-21 | 2025-04-21 | 2025-05-12 | 2025-06-02 | 2025-06-23 |  | NO | NA
HR | 56 | Framework contract for supply of personal protective equipment | 250000000 | EUCL | SS | 2024-11-01 | 2024-11-22 | 2024-12-22 | 2024-12-22 | 2025-01-12 | 2025-02-02 | 2025-02-23 |  | NO | NA
CORPORATE SERVICES | 57 | Hiring a private land surveying services | 20000000 | EUCL | NCB | 2024-08-01 | 2024-08-22 | 2024-09-21 | 2024-09-21 | 2024-10-12 | 2024-11-02 | 2024-11-23 |  | NO | NA
CORPORATE SERVICES | 58 | Provision of Valuation Services | 15000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
LEGAL | 59 | Hiring Local/national lawyers to represent EUCL in court under Framework Contract | 75000000 | EUCL | NCB | 2024-09-01 | 2024-09-22 | 2024-10-22 | 2024-10-22 | 2024-11-12 | 2024-12-03 | 2024-12-24 |  | NO | NA
LEGAL | 60 | hiring Professional Court Bailiffs to execute Judgements and other Judicial Decisions for EUCL under Framework Contract | 20000000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
HR | 61 | Hiring company/Clinic for Mental health awareness to EUCL staff | 51800000 | EUCL | NCB | 2024-10-01 | 2024-10-22 | 2024-11-21 | 2024-11-21 | 2024-12-12 | 2025-01-02 | 2025-01-23 |  | NO | NA
Formulas:
Publication = [Tender Doc Preparation]+21
opening = +[Publication]+30
Start Evaluation = [opening]
End evaluation = [Start Evaluation]+21
Final Notification = [End evaluation]+21
Contract Signature Date = [Final Notification]+21
Note on F2: Kevin Irankunda: Internation Competion ¦Bidding
Note on F3: Kevin Irankunda: National Competion ¦Bidding
Note on F6: Kevin Irankunda: Request for Expresiion of Interest